Project: Symbiotic Networks of Bio-Waste Sustainable Management (SYMBIOSIS)

TERMS OF REFERENCE

Mapping bio-waste streams in CBC area, and 
Record the needs of cross-sectoral industries in CBC area

Introduction

SYMBIOSIS project proposes an integrated approach to the management and utilization of organic residues. The term organic waste does not mean only the organic portion of urban waste but more importantly agricultural residues and animal breeding facilities that are basically an untapped potential. The main challenge of the project is to reconcile the bio-waste output with demand in cross sectorial industries for use either as a feedstock or as fuel. This will be done with the detailed record of producers and potential users and the achievements of business agreements. Aim also is the examination of End-life solutions such as composting for the exploitation of organic waste as fertilizer, to control the waste flows in order to reduce the disposal of organic materials that are driven to the landfills. Currently, the utilization of organic waste is almost zero without a complete project proposal development for the use and exploitation of those material.

The intention of Symbiosis is to change that completely. This will become by the platform of SYMBIOSIS project basis of experience of the National Technical University of Athens which has expertise in the development and operation of such tool that will suggest the optimal utilization, estimating the cost of transport and material handling. Industrial Symbiosis (IS) is an innovative approach that will bring together companies from all business sectors with the aim of improving cross industry resource efficiency through the commercial trading of materials, energy and water and sharing assets, logistics and expertise. The platform will consist a powerful technological tool that can manage the waste flows (characterized by types, locations, volumes and seasonality) in relation with the costs of acquisition, and transportation, also taking into account the environmental burden, to provide accountable bioenergy networks and increase cross-industry resource efficiency. The main deliverables will be a detailed record of all flows in area CBC bio-waste as well as the identification of potential users? The SYMBIOSIS platform will be used for matching between supply and demand of bio-waste? The Action Plans for the utilization of organic waste and the interface with Regional Operational Programmes? Studies on the economic and environmental benefits as well as the measures towards a Circular Economy in the CBC area; In addition, substantial large-scale pilot applications will be developed with the use of bio-containers and Green bins. Beneficiaries will be companies making use of bio-waste as a resource, agricultural and livestock farming, local municipalities and citizens of client application areas. The innovation of the project lies in the Symbiosis platform and comprehensive approach aimed at concluding agreements real utilization of organic residues. The added value is measured in financial resources, in improving the environment and the creation of new jobs.

SYMBIOSIS Project Identification

Greece produces more than 4.5 million tons of residential and commercial urban waste annually with commercial and industrial waste steadily increasing. This is equivalent to 440 kilograms per person. The fYR of Macedonia on the other hand, produces more than 750 ktons of urban waste equivalent of around 350kg/person. At the area of question only 5-6% of waste is recycled in the Greek part, where on the other side of the borders is about 1%. In both regions no treatment or use of organic waste is made; all the bio-waste is led to the landfills. Apart from urban waste, both regions are characterized by large extent of agricultural activities which produce large quantities of agro-waste but also important quantities of manure from animal breeding (estimated at 100ktons/year in Florina district and 70 ktons/year in Bitola and Novaci district areas). Again, no special treatment or exploitation of that material is made. Apart from some quantities of residues like straw, that is used in the form of silage for animal feeding, all other organic material is either burnt or partly used as fertilizer (in the case of animal waste).

On the other hand, the ‘users’ of bio-waste e.g. fodder, district heating, bioenergy, fertilizer, greenhouses etc. companies and agricultural processing businesses are very much interested to find and use those wastes either as a raw material or as a fuel to their activities.

Industrial Symbiosis (IS) is an innovative approach that brings together companies from all business sectors with the aim of improving cross industry resource efficiency through the commercial trading of materials, energy and water and sharing assets, logistics and expertise. In order to achieve this, a powerful technological tool will be developed that can manage the waste flows (characterized by types, locations, volumes and seasonality) in relation with the costs of acquisition and transportation, also taking into account the environmental burden, to provide accountable bioenergy networks and increase cross-industry resource efficiency. Symbiosis capitalizes the knowledge on symbiotic practices (eSymbiosis), the Symbiosis bioenergy network in Thessaly (AI4B- www.ai4b.gr/), the biomass processing routes for regional development (BIOCORE/FP7 on lignocellulosic biomass, GABE project for the biomass exploitation in CBC area) and a long list of models and knowledge available on processing paths.

By changing behavior and common practices against wastes and turning waste into a resource, SYMBIOSIS offers a key to a circular economy in the CBC project area. The objectives and targets set in the 7th Environment Action Plan, are the key drivers of SYMBIOSIS project for the improvement of waste management, stimulate innovation in recycling, promote trade and use of bio-waste, limit the waste lead to landfills, and create incentives to change consumer behavior.

SYMBIOSIS promotes re-manufacturing, reuse and recycle, and transforms one industry's waste to another's raw material and/or fuel, to pave the way for a more circular economy for the regions, where waste is eliminated and resources are used in an efficient and sustainable way. The direct beneficiaries of Symbiosis project will be the ‘producers’ and ‘users’ of bio-wastes that include a large number of companies and agro-industries inside the cross-border area. The common platform of SYMBIOSIS project will meet the ‘offer’ with the ‘demand’ of bio waste creating synergies and business opportunities providing new solution for exploitation of bio-waste. Scope is the real matching of those companies and the sign of cooperation agreements among them. Moreover, the local authorities responsible for waste management will conduct pilot testing for the exploitation of urban and agro-waste and will develop their Action Plans for bio-waste management and separate treatment. Last but not least, experts will conduct studies on the environmental and economic impact of the project to the participated regions.

Objectives of SYMBIOSIS Project

The project main objective is to set up an integrated, sustainable, bio-waste management and trading scheme between the partner regions of Western Macedonia in Greece (former pref. of Florina) and the municipality areas of Bitola and Novaci in the former Yugoslav Republic of Macedonia following the Industrial Symbiosis concept. SYMBIOSIS will develop symbiotic networks bringing together companies and stakeholders from all business sectors, aiming to improve cross industry resource efficiency through material trading and sharing assets in an environmentally sustainable way.

Planning and regional development infrastructures, and matchmaking and retrieval services are key means in SYMBIOSIS to set up cost-effective biomass supply chains. The project specific objectives are:

1. To set-up a cross industry resource efficiency through organic material trading and sharing assets;

2. To create industrial sustainable networks especially in the agro-food industry;

3. To achieve maximum efficiencies in energy and water use;

4. To have a reference point where the demand will meet the offer of bio-waste materials in CBC area;

5. To improve the local policies on the management of bio-waste streams and tackle this issue individually following the directions of the EU policy for less bio-waste to the landfills and better utilization for other uses;

6. To improve the environmental benefits by reducing the bio-waste streams that were disposed into landfills;

7. To generate tangible social benefits to local communities by better use of bio resources from the food industry in favour to social activities;

8. To improve the cooperation among sectors and businesses in cross-border area thus improving the local economies and boosting entrepreneurship;

9. To support the local economies by safeguarding raw materials or fuel coming from bio-waste;

10. To promote job creation in the regions into question by exploring the trade opportunities and using the waste as a resource.

Expected Results of SYMBIOSIS Project

1) Create new employment in bio-waste sector. According to international standards measuring the impact to the employment on the bio-waste sector, at least 1 person will be employed for the execution of the agreement between a bio-waste producer and a bio-waste user. Therefore, if the project succeeds 10 such agreements (in a conservative case) in CBC area this result in the creation of 10 new jobs.

2) Create implementation strategies on a decision-making level. Due to the development of an Action Plan for exploitation of bio-waste resources in the target regions, the promotion of bio-waste business will flourish creating benefits for the local businesses and the local communities binding the local Action Plans with the National Waste Management Plans.

3) Reducing of bio-waste lead to the landfills. Bio-waste is not for disposal. Therefore, through the implementation of the pilot activities, the overall bio-waste will decrease, creating useful fertilizer for the agricultural activities.

More importantly, the pilot demonstration activities will show the way towards the integrated and sustainable solutions in bio-waste management and treatment.

4) Create economic benefits through the use of a powerful networking tool, the Symbiosis platform. Through the Symbiosis platform every company operating in the area will have the ability to go through the platform and to examine business opportunities raised by finding and securing cheap raw material for his/her business. Apart from the resource information, cost analysis of transfer, handling and process will be available.

5) Reducing the environmental burden. For every ton of bio-waste that is not lead to the landfill or it is not burn in open-fires at the field, there is a reduction in Carbon dioxide (CO2) and/or methane (CH4) emitted to the atmosphere. If we set a target for better treatment of 10.000tons/year in the CBC area this results to 300 tons reduction of methane emissions or 6300 CO2 tons eq.

Methodological Approach of SYMBIOSIS Project

The SYMBIOSIS Project is realized in 6 Work Packages (WP)

WP1: Project Management & Coordination

Scope of this WP is the smooth and on track project implementation, the continuous control and monitoring of project progress and the necessary adaptations and adjustments of the project plan if it is deemed necessary.

1.2 Day-to-day project management and coordination.

  - Delivery of project reports including all project achievements, measurable outputs and immediate results.

  - Development and analytical work plan including the time plan for action (Gantt chart).

WP2: Communication and Dissemination Activities

Scope of this WP is to communicate the project results to the local stakeholders and the direct beneficiaries of the project tools and capabilities. In addition, priority set to the establishment of a public dialogue with the local communities and their sensitization about bio-waste treatment and exploitation.

2.1 Establishment of a social dialogue and training sessions.

  - Set up a database of direct and indirect beneficiaries to get informed through electronic newsletters (in quarter basis, total 8).

  - Development a communication hub including an Official Project Site, at least 3 links with social media, 4 articles in semester basis, newsroom, link with Symbiosis platform.

  - Preparation, organization and execution of the Final Project Conference in Bitola. Development of an information booklet (including a leaflet, a booklet of main project results, 1 DVD with deliverables, a memory stick of 200 copies each).

WP3: Collection and management of data for bio-waste streams

The scope of this WP is to collect all on-the-spot info about bio-waste production and its use.

After the collection of the information an analysis will take place about the benefits in economic and environmental terms from the implementation of cross sectoral bio-waste use. This WP includes:

3.1. Mapping, measurement of all bio-waste streams derived by agro-food industrial sector (outflow).

3.2. Record and analyze the needs of the cross-sectoral industries of raw materials and wood-based resources e.g. greenhouses (inflow).

3.3. Study of the economic benefits to the regional economies by the operation of the Symbiosis platform;

3.4. Examine and study the environmental benefits of the Symbiosis network;

WP 4: Develop and operate the Symbiosis platform

Scope of this WP is the development of a powerful tool for achieving resource efficiency in CBC area. It includes:

4.1 The development of the Symbiosis platform with data integration from WP3;

4.2 Test and operation of the Symbiosis Platform;

4.3. Match-making of offer and demand of bio-waste streams in cross-sectorial level in the Greek project area;

4.4 Prepare the template of the legally binding bio-waste agreement and proceed with the match-making & business agreements in the fYR of Macedonia project area;

4.5 Training of local stakeholders for the use of the platform and continuous update;

WP5: Develop an Action Plan for bio-waste exploitation

5.1 Report on the national policies on Waste Management and the current level of their implementation in regional level. Explain the poor results in bio-waste treatment and recycling;

5.2 Develop an Action Plan for the integration of Symbiosis networks to the regional strategies;

5.3 Towards Circular Economy: How bio-waste fully exploitation could support employment & reg. GDP's.

WP6: Pilot activities of waste composting

6.1 Technical study on composting procedure/facility in Bitola

6.2 Perform all necessarily procurement of equipment, materials and work;

6.3 Supply the equipment and bring it in operational level

6.4 Training the personnel to use the composters and waste vehicle;

6.5 Set-up the organic composters to the selected areas. Make a pilot implementation of the composting units for 6m. Report of the operation.

SYMBIOSIS Project Partners (fYR of Macedonia):

The SYMBIOSIS project is implemented by three partners in the former Yugoslav Republic of Macedonia (PE Komunalec – Bitola, PCE Komunalna Higiena – Novaci, and Movement for Environment Molika DOM – Bitola) and three partners from Greece (Waste Management of Western Macedonia DIADYMA SA, InnoPolis - Centre for Innovation and Culture, National Technical University in Athens).

Public Communal Enterprise KOMUNALEC Bitola, established in 1996, performs public works in Municipality of Bitola (95.000 citizens). Being the second largest waste management company in the country, 253 employees, PE Komunalec is recognized by its highly professional technical staff, institutional and financial capacities that lead us to mutual decision this organization to be appointed as LB of the project.

Public Communal Enterprise KOMUNALNA HIGIENA Novaci, located in the rural area of Pelagonia Region, is relatively young waste management enterprise, performing public communal services in Municipality of Novaci (4000 citizens). The municipalities are responsible for organization of collection, transportation and disposal of municipal wastes; supervising transportation and disposal of industrial non-hazardous waste; deciding on locations of waste management facilities, issuing local regulations on waste management facilities; issuing environmental permits (IPPC B-permits).

Both enterprises have active presence and influence on local and regional policies by well-established cooperation with local authorities and relevant stakeholders from the business sector and professionals related to waste management and environmental issues. They have been actively involved within development of municipal strategic documents such as Action Plan for environment protection Bitola Municipality-2015, Plan for Waste Management-Novaci Municipality 2014-2019, National Strategy for Waste Management 2008-2020, etc.

CSO Movement for Environment MOLIKA Bitola works on raising public awareness on environmental issues and preservation of environment. The CSO has implemented many projects such as Citizens’ initiative-changing the Law on air quality, Green Phone, Conservation of National Park Pelister, Study on water quality in Bitola, etc.

ASSIGNMENTS OF THE CONTRACTOR

Lot 1: Mapping bio-waste streams in CBC area

The external contractor should map the potential sources of bio-waste on the territory of the municipalities of Bitola and Novaci from industrial, agricultural and other companies. The map should contain the following information:

- Location

- Type of organic waste

- Estimated quantities

- Current state (way of waste treatment)

The map should be interactive and accessible via the web, as well as documented in adequate study about mapping bio-waste streams in CBC area (Municipalities Bitola and Novaci).

Tasks of the contractor includes, but are not limited to: Development of methodology for identification of different types of bio-waste streams; identification and mapping of qualitative and quantitative data of specific waste streams, supported with details regarding the type of waste, characteristics such are the main waste components, moisture, density, gauge, quantities available, seasonal variations, frequency, location, current way of treatment and/or disposal, market value, transport costs, etc.; development of methodology for data collection, conducting survey, organization of meetings with relevant stakeholders, data processing and defining results.

Lot 2: Record the needs of cross-sectoral industries in CBC area

The external contractor should record and analyze the needs of the cross-sectoral industries of raw materials and wood-based resources. The analysis should be presented in a study which will assess:

- Needs of cross-sectoral industries the CBC area (Municipalities Bitola and Novaci) for (bio) raw materials and wood-based resources.

- Possibilities for establishing local market of reused (bio) raw materials and wood-based resources (e.g. compost)

- Possibilities for exporting in CBC area (Greek part) reused (bio) raw materials and wood-based resources (e.g. compost), and exporting internationally.

Tasks of the contractor includes, but are not limited to: identification of the current situation regarding the needs of the cross-sectoral industries for different types of bio-wastes supported with relevant data of different types of specific organic materials needed (moisture, density, gauge, production capacities/quantities,  frequency, location, market value, etc.); data collection (example: questionnaires); recommendations for key priorities and potentials for fostering of circular economy, development of report.

DURATION OF ASSIGNMENT

Both assignments (Lot 1 and Lot 2) should be completed in three months after signing the contract.